## Weekly Budget
Under Buget
Weekly Budget |  |  | Over Budget
Week 3
| Allocated $ | Used $ | Over/Under $
Man hours | #REF! | #REF! | #REF!
Hardware | 50 | 8 | 42
Overheads | 200 | 200 | 0
Total $$ | #REF! | #REF! | #REF!
Cuml YTD $$ | #REF! | #REF! | #REF!
Week 2
| Allocated $ | Used $ | Over/Under $
Man hours | #REF! | #REF! | #REF!
Hardware | 50 | 14 | 36
Overheads | 200 | 200 | 0
Total $$ | #REF! | #REF! | #REF!
Cuml YTD $$ | #REF! | #REF! | #REF!
Week 1
| Allocated $ | Used $ | Over/Under $
Man hours | #REF! | #REF! | #REF!
Hardware | 1400 | 1210 | 190
Overheads | 200 | 200 | 0
Total $$ | #REF! | #REF! | #REF!
Cuml YTD $$ | #REF! | #REF! | #REF!
1210
Week 4
| Allocated $ | Used $ | Over/Under $
Man hours | #REF! | #REF! | #REF!
Hardware | 50 | 0 | 50
Overheads | 200 |  | 200
Total $$ | #REF! | #REF! | #REF!
Cuml YTD $$ | #REF! | #REF! | #REF!

## Scheduel
| Start Date | Completed | Remaining
Structure (BADS) | 2007-10-29 | 19 | 2
Navigation (NAS) | 2007-10-29 | 19 | 4
Recognition (BOReS) | 2007-10-29 | 19 | 1
NAS/BOReS Merger | 2007-11-15 | 2 | 3
Full system integration | 2007-11-15 | 2 | 4
Debugging | 2007-11-15 | 2 | 8

## Man Hours
Team Echo
Budget
Average wage:($/h)
Man Hours
Usage | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Structure | 18 | 18 | 18 | 15 | 0
Used | 10 | 15 | 6 | 11 | 0
Navigation | 20 | 20 | 20 | 20 | 0
Used | 8 | 6 | 25 | 26
Recognition | 20 | 20 | 20 | 20 | 0
Used | 7 | 7 | 23 | 28 | 0
Integration | 0 | 0 | 0 | 0 | 15
Used | 0 | 0 | 0 | 0 | 38
Debugging | 0 | 0 | 0 | 0 | 15
Used | 0 | 0 | 0 | 0 | 47
Paper work | 2 | 2 | 2 | 5 | 0
Used | 2 | 2 | 7 | 5 | 0
Over/Under | 34 | 30 | -1 | -10 | -55
YTD | 34 | 64 | 63 | 53 | -2
Week 2 | Time Allocation
Usage | Hours
Meeting | 6 |  | Week 1 | Time Allocation |  | Time Used
Structure | 18 |  | Usage | Hours | Cost | Hours | Cost
Navigation | 20
Recognition | 20 |  | Structure | 18 | 0 | 10 | 0
Paper work | 2 |  | Navigation | 20 | 0 | 8 | 0
Total | 66 | #REF! | Recognition | 20 | 0 | 7 | 0
|  |  | Paper work | 2 | 0 | 2 | 0
Week 3 | Time Allocation |  | Total | 60 | 0 | 27 | 0
Usage | Hours
Meeting | 6 |  | Week 2 | Time Allocation |  | Time Used
Structure | 18 |  | Usage | Hours | Cost | Hours | Cost
Navigation | 20
Recognition | 20 |  | Structure | 18 | 0 | 15 | 0
Paper work | 2 |  | Navigation | 20 | 0 | 6 | 0
Total | 66 | #REF! | Recognition | 20 | 0 | 7 | 0
|  |  | Paper work | 2 | 0 | 2 | 0
Week 4 | Time Allocation |  | Total | 60 | 0 | 30 | 0
Usage | Hours
Meeting | 6 |  | Week 3 | Time Allocation |  | Time Used
Structure | 5 |  | Usage | Hours | Cost | Hours | Cost
Navigation | 20
Recognition | 20 |  | Structure | 18 | 0 | 6 | 0
Integration | 10 |  | Navigation | 20 | 0 | 25 | 0
Paper work | 5 |  | Recognition | 20 | 0 | 23 | 0
Total | 66 | #REF! | Paper work | 2 | 0 | 7 | 0
|  |  | Total | 60 | 0 | 61 | 0
Week 5 | Time Allocation
Usage | Hours
Meeting | 3
Structure | 0
Navigation | 0
Recognition | 0
Integration | 15
Debugging | 15
Total | 33 | #REF!

## Hardware
Week | Item | Qty | Cost/Unit | Total $
1 | NXT Kit | 3 | 400 | 1200
| Batteries (4pk) | 2 | 5 | 10
|  |  | Total | 1210
Week | Item | Qty | Cost/Unit | Total $
2 | 16AWG wire (feet) | 2 | 2 | 4
| Network female plug | 1 | 4 | 4
| Diodes | 3 | 2 | 6
|  |  | Total | 14
Week | Item | Qty | Cost/Unit | Total $
3 | Breadboard and wires | 1 | 4 | 4
| Chip | 2 | 5 | 4
0
|  |  | Total | 8