## Weekly Budget
Under Buget
Weekly Budget |  |  | Over Budget
Week 3
| Allocated $ | Used $ | Over/Under $
Man hours | 2310 | 2415 | -105
Hardware | 50 | 8 | 42
Overheads | 200 | 200 | 0
Total $$ | 2560 | 2623 | -63
Cuml YTD $$ | 9030 | 6662 | 3776
Week 2
| Allocated $ | Used $ | Over/Under $
Man hours | 2310 | 1260 | 1050
Hardware | 50 | 14 | 36
Overheads | 200 | 200 | 0
Total $$ | 2560 | 1474 | 1086
Cuml YTD $$ | 6470 | 4039 | 2690
Week 1
| Allocated $ | Used $ | Over/Under $
Man hours | 2310 | 1155 | 1155
Hardware | 1400 | 1210 | 190
Overheads | 200 | 200 | 0
Total $$ | 3910 | 2565 | 1345
Cuml YTD $$ | 3910 | 2565 | 1345
1210
Week 4
| Allocated $ | Used $ | Over/Under $
Man hours | 2310 | 0 | 2310
Hardware | 50 | 0 | 50
Overheads | 200 |  | 200
Total $$ | 2560 | 0 | 2560
Cuml YTD $$ | 11590 | 6662 | 3713

## Scheduel
| Start Date | Completed | Remaining
Structure (BADS) | 2007-10-29 | 19 | 2
Navigation (NAS) | 2007-10-29 | 19 | 4
Recognition (BOReS) | 2007-10-29 | 19 | 1
NAS/BOReS Merger | 2007-11-15 | 2 | 3
Full system integration | 2007-11-15 | 2 | 4
Debugging | 2007-11-15 | 2 | 8

## Man Hours
Team Echo
Budget
Average wage:($/h) |  |  | 35
Man Hours
Week 1 | Time Allocation |  | Time Used
Usage | Hours | Cost | Hours | Cost
Meeting | 6 | 210 | 6 | 210
Structure | 18 | 630 | 10 | 350
Navigation | 20 | 700 | 8 | 280
Recognition | 20 | 700 | 7 | 245
Paper work | 2 | 70 | 2 | 70
Total | 66 | 2310 | 33 | 1155
Week 2 | Time Allocation |  | Time Used
Usage | Hours | Cost | Hours | Cost
Meeting | 6 | 210 | 6 | 210
Structure | 18 | 630 | 15 | 525
Navigation | 20 | 700 | 6 | 210
Recognition | 20 | 700 | 7 | 245
Paper work | 2 | 70 | 2 | 70
Total | 66 | 2310 | 36 | 1260
Week 3 | Time Allocation |  | Time Used
Usage | Hours | Cost | Hours | Cost
Meeting | 6 | 210 | 8 | 280
Structure | 18 | 630 | 6 | 210
Navigation | 20 | 700 | 25 | 875
Recognition | 20 | 700 | 23 | 805
Paper work | 2 | 70 | 7 | 245
Total | 66 | 2310 | 69 | 2415

## Hardware
Week | Item | Qty | Cost/Unit | Total $
1 | NXT Kit | 3 | 400 | 1200
| Batteries (4pk) | 2 | 5 | 10
|  |  | Total | 1210
Week | Item | Qty | Cost/Unit | Total $
2 | 16AWG wire (feet) | 2 | 2 | 4
| Network female plug | 1 | 4 | 4
| Diodes | 3 | 2 | 6
|  |  | Total | 14
Week | Item | Qty | Cost/Unit | Total $
3 | Breadboard and wires | 1 | 4 | 4
| Chip | 2 | 5 | 4
0
|  |  | Total | 8